## P1C2 Functional Specifications
Synthesis | Questions | Points of attention
The goal of the project is to evolve the website of the company "Nous sommes à la page" to allow its customers to buy its products directly from the site rather than having to call the sales representatives. To do this, it is planned, in version 1.0.0 of the CLC project, that two new interfaces and a new database table will be created. The first interface will offer a form to select the characteristics of the product. This information will be saved in the database. And a second interface will allow you to track the progress of the order. | Do the specifications describe the behavior that the system should have, but do not give any indication of the visual rendering that the two new interfaces should have? | NS-7: The acceptance criteria are not precise enough. What are the expected results?

## P1C3 Requirements and Functionality
Requirement | Typology | Criticality | Functionality
example: NS-01 | UI | Critical | Order reception
NS-5 | UI | Average | Order reception
NS-6 | Back-office | Critical | Order reception
NS-7 | UI | Average | Order tracking

## P1C4 Requirements Review V1
Question number | Requirement | Applicant | Criticality | Request date | Comment | State | Document version | Respondent | Response date | Response
1 | EX-1 | Martin | Critical | 2023-01-02 | A typo must have slipped in instead of the WS URL? | Processed | v.1 | Adrien | 2023-01-09 | Updated spec
1 | NS-5 | You | Average | 2023-04-20 | In the acceptance criteria, the elements to be checked for the "Cancel" button are not described. What about it? | Sent | v.1 | Édouard | 2023-04-24 | Specifications to be updated in this direction: "When clicking on "Cancel", verify that the data is not saved in the database. Then that the user returns to the previous screen."
2 | NS-6 | You | Critical | 2023-04-20 | The format of the "Adr_livr" field is not specified, what type should it be? | Sent | v.1 | Édouard | 2023-04-24 | Spec to be updated: the format must be of type TEXT.
3 | NS-7 | You | Critical | 2023-04-20 | The specification indicates the information that must be displayed, but does not describe where it should be searched? | Sent | v.1 | Édouard | 2023-04-24 | Spec to be updated: This information must be retrieved from the database. The customer name must come from the t_client table, "Nom" field. Customer identifier from t_client, "id_client" field. Order number from t_commande, "id_commande" field. The delivery address from t_commande, "Adr_livr" field.
Email sharing the deliverable
To: MOA, AMOA, PO CC: Project team Subject: Delivery of requirements review document
Hello, You will find attached to this email the requirements review document. Here are the key points to remember: - Requirement NS-6: The format of a field in the database is not specified. - Requirement NS-7: The specifications do not indicate where to retrieve the information in the database. I draw your attention to these warning elements: - Requirement NS-5: The acceptance criteria do not mention what should be checked for the "Cancel" button. I remain at your disposal for any further information, Sincerely, ME

## P1C5 Deliverable Email
Requirement | Applicant | Criticality | Request date | Comment | State | Document version | Respondent | Response date | Response
EX-1 | Martin | Critical | 2023-01-02 | A typo must have slipped in instead of the WS URL? | Processed | v.1 | Adrien | 2023-01-09 | Updated spec
NS-5 | You | Average | 2023-04-20 | In the acceptance criteria, the elements to be checked for the "Cancel" button are not described. What about it? | Processed | v.1 | Édouard | 2023-04-24 | Specifications to be updated in this direction: "When clicking on "Cancel", verify that the data is not saved in the database. Then that the user returns to the previous screen."
NS-6 | You | Critical | 2023-04-20 | The format of the "Adr_livr" field is not specified, what type should it be? | Processed | v.1 | Édouard | 2023-04-24 | Spec to be updated: The format must be of type TEXT.
NS-7 | You | Critical | 2023-04-20 | The specification indicates the information that must be displayed, but does not describe where it should be searched? | Processed | v.1 | Édouard | 2023-04-24 | Spec to be updated: This information must be retrieved from the database. The customer name must come from the t_client table, "Nom" field. Customer identifier from t_client, "id_client" field. Order number from t_commande, "id_commande" field. The delivery address from t_commande, "Adr_livr" field. For the part of the order details, I must validate something before I can answer.
NS-7 | You | Critical | 2023-04-21 | Édouard's response: For the display of the request details, this has not been specified. Point taken with the developers. | Sent | v.2
Final Deliverable Email
To: MOA, AMOA, PO CC: Project team Subject: Delivery of requirements review document
Hello, Please find attached the final requirements review document. Here are the key points to remember: The issues raised on NS-5, NS-6, and some of those on NS-7 have been resolved. I draw your attention to this alert: - Requirement NS-7: The storage method for the detail of the request, including its content and progress status, has not been specified. Édouard has taken this point to define it. Please do not hesitate to contact me if you require any further information. Kind regards, ME