## P1C2 Functional Specifications
Synthesis | Questions | Points of attention
The goal of the project is to evolve the website of the company "Nous sommes à la page", in order to allow its customers to buy its products directly from the site rather than having to call the sales representatives. To do this, it is planned, in version 1.0.0 of the CLC project, that two new interfaces and a new table in the database will be created. The first interface will offer a form to select the characteristics of the product. This information will be saved in the database. And a second interface will allow to follow the progress of the order. | Do the specifications describe the behavior that the system should have, but do not give any indication of the visual rendering that the two new interfaces should have? | NS-7: The acceptance criteria are not precise enough. What are the expected results?

## P1C3 Requirements and Functionalities
Requirement | Typology | Criticality | Functionality
example: NS-01 | HMI | Critical | Order reception
NS-5 | HMI | Average | Order reception
NS-6 | Back-office | Critical | Order reception
NS-7 | HMI | Average | Order tracking

## P1C4 Requirements Review V1
Question number | Requirement | Applicant | Criticality | Request date | Comment | State | Document version | Respondent | Response date | Response
1 | EX-1 | Martin | Critical | 2023-01-02 | A typo must have slipped in instead of the WS URL? | Processed | v.1 | Adrien | 2023-01-09 | Updated spec
1 | NS-5 | You | Average | 2023-04-20 | In the acceptance criteria, the elements to be checked for the "Cancel" button are not described. What about it? | Sent | v.1 | Édouard | 2023-04-24 | Specifications to be updated in this direction: "When clicking on "Cancel", verify that the data is not saved in the database. Then that the user returns to the previous screen."
2 | NS-6 | You | Critical | 2023-04-20 | The format of the "Adr_livr" field is not specified, what type should it be? | Sent | v.1 | Édouard | 2023-04-24 | Spec to be updated: the format must be of type TEXT.
3 | NS-7 | You | Critical | 2023-04-20 | The specification indicates the information that must be displayed, but does not describe where it should be searched? | Sent | v.1 | Édouard | 2023-04-24 | Spec to be updated: This information must be retrieved from the database. The Customer Name must come from the t_client table, "Nom" field. Customer ID from t_client, "id_client" field. Order number from t_commande, "id_commande" field. The delivery address from t_commande, "Adr_livr" field.
Mail of the deliverable sharing
To: MOA, AMOA, PO CC: Project team Subject: Delivery of requirements review document
Hello, You will find attached to this email the requirements review document. Here are the key points to remember: - Requirement NS-6: The format of a field in the database is not specified. - Requirement NS-7: The specifications do not indicate where to retrieve the information in the database. I draw your attention to these warning elements: - Requirement NS-5: The acceptance criteria do not mention what should be checked for the "Cancel" button. I remain at your disposal for any further information, Sincerely, ME

## P1C5 Deliverable Email
Requirement | Applicant | Criticality | Request date | Comment | State | Document version | Respondent | Response date | Response
EX-1 | Martin | Critical | 2023-01-02 | A typo must have slipped in instead of the WS URL? | Processed | v.1 | Adrien | 2023-01-09 | Updated spec
NS-5 | You | Average | 2023-04-20 | In the acceptance criteria, the elements to be checked for the "Cancel" button are not described. What about it? | Processed | v.1 | Édouard | 2023-04-24 | Specifications to be updated in this direction: "When clicking on "Cancel", verify that the data is not saved in the database. Then that the user returns to the previous screen."
NS-6 | You | Critical | 2023-04-20 | The format of the "Adr_livr" field is not specified, what type should it be? | Processed | v.1 | Édouard | 2023-04-24 | Spec to be updated: The format must be of type TEXT.
NS-7 | You | Critical | 2023-04-20 | The specification indicates the information that must be displayed, but does not describe where it should be searched? | Processed | v.1 | Édouard | 2023-04-24 | Spec to be updated: This information must be retrieved from the database. The Customer Name must come from the t_client table, "Nom" field. Customer identifier from t_client, "id_client" field. Order number from t_commande, "id_commande" field. Delivery address from t_commande, "Adr_livr" field. For the order details part, I need to validate something before I can answer.
NS-7 | You | Critical | 2023-04-21 | Édouard's response: The display of the request details was not specified. Point taken with the developers. | Sent | v.2
Email of the final deliverable
To: MOA, AMOA, PO CC: Project team Subject: Delivery of requirements review document
Hello, Please find attached to this email the final document of the requirements review. Here are the key points to remember: The elements identified on NS-5, NS-6, and part of those on NS-7 have been resolved. I draw your attention to this alert element: - Requirement NS-7: The storage method for the request details with its content and progress has not been specified. Point taken by Édouard to define this. I remain at your disposal for any further information, Sincerely, ME

## P2C1 Scenario Definition
Functionality | Requirements | Scenario | Comment | Impact
Order reception | NS-5 | - Registration of an authenticated customer order - Cancellation of an order entry | CDT-2 will become obsolete with this project. It will not be possible to place an order without being authenticated. | CDT-2: Place a customer order without authentication CDT-3: Place an authenticated customer order Autom-2: Place a customer order without authentication Autom-3: Place an authenticated customer order
Order reception | NS-6 | - Verification of the t_commande table | This table still needs to evolve to take into account the order details. Wait for Édouard's feedback before building the scenario.
Order tracking | NS-7 | - Verification of order tracking

## P2C2 Test Methods
Scenario related to the functionality | Test method | Justification
Registration of an authenticated customer order | Black box | As test automations may not be available for the start of the campaign, the tests will be performed manually.
Registration of a customer order without authentication | Black box
Cancellation of an order entry | Black box
Verification of the t_commande table | Black box
Verification of order tracking | Black box
"Order Reception" functionality - Exploratory tests | Exploratory tests | Exploratory testing session to improve test coverage.
"Order Tracking" functionality - Exploratory tests | Exploratory tests | Exploratory testing session to improve test coverage.
Customer area access | Non-regression | Critical functionality of the application, it is necessary to perform a non-regression test to verify that it has not suffered any side effects.

## P2C3 Resource Inventory
Scenario related to the functionality | Environment | Justification | Tester | Justification | Test tool | Justification | Test data | Justification
- Registration of an authenticated customer order - Cancellation of an order entry - Verification of the t_commande table - Verification of order tracking | ENV-2 | ENV-1 will not be available during the execution phase | You | Of the two available resources, Andy will be on leave for most of the execution phase and will be on another project afterwards. As for me, the 2 days of absence will have a very minimal impact during the phase. | Excel | Use of the existing test management tool in the company. The other tool being tested by the other team is not official, it cannot be used. | DUPONT
- Registration of a customer order without authentication | ENV-2 | ENV-1 will not be available during the execution phase | You | Of the two available resources, Andy will be on leave for most of the execution phase and will be on another project afterwards. As for me, the 2 days of absence will have a very minimal impact during the phase. | Excel | Use of the existing test management tool in the company. The other tool being tested by the other team is not official, it cannot be used. |  | No test data required. The test case is performed in "non-authenticated" mode.

## P2C4 Step Planning
|  | October | [30 empty] | November
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Developments | bar: October 3 to October 7; October 10 to October 14
Tests | Requirements analysis | bar: October 3 to October 7
Test strategy | bar: October 10 to October 12
Design | bar: October 13 to October 14
Execution | bar: October 17 to October 20; October 25 to October 28
Report | bar: October 31
Production release | bar: November 21
Absences | Andy | bar: October 17 to October 21; October 24 to October 28
You | bar: October 21; October 24

## P2C5 Recommendation
Recommendation email
To: MOA, AMOA, PO CC: Project team Subject: Recommendation | Hello, Please find attached to this email the test strategy concerning the CLC project in version 1.0.0. Here are the key points to remember: - Test automates cannot be used during the execution phase. They will need to be updated following the test campaign. - Andy's vacation during the execution phase. I draw your attention to these warning elements: - The solution for recording order information arrived only 3 days before the end of development. This presents a risk of delaying the start of execution. --> This risk could be absorbed by the significant delay (1 month) between the planned end of execution and the production release. I remain at your disposal for any further information, Sincerely, ME
Hello, Please find attached to this email the test strategy concerning the CLC project in version 1.0.0. Here are the key points to remember: - Test automates cannot be used during the execution phase. They will need to be updated following the test campaign. - Andy's vacation during the execution phase. I draw your attention to these warning elements: - The solution for recording order information arrived only 3 days before the end of development. This presents a risk of delaying the start of execution. --> This risk could be absorbed by the significant delay (1 month) between the planned end of execution and the production release. I remain at your disposal for any further information, Sincerely, ME

## P3C1 Preparation of Specific
Requirement ID | Requirement name | Version | Criticality | Status | Category | Description
NS-5 | Order UI | v1 | Major | Approved | Functional | Order UI to allow customers to order and receive their orders.
NS-6 | Order table | v1 | Major | Approved | Technical | Database table to store order information.
NS-7 | Tracking UI | v1 | Major | Approved | Functional | Tracking UI to allow customers to track their order.