## P1C2 Functional Specifications
Synthesis | Questions | Points of attention
The goal of the project is to evolve the website of the company "Nous sommes à la page", in order to allow its customers to buy its products directly from the site rather than having to call the sales representatives. To do this, it is planned, in version 1.0.0 of the CLC project, that two new interfaces and a new table in the database will be created. The first interface will offer a form to select the characteristics of the product. This information will be saved in the database. And a second interface will allow you to track the progress of the order. | Do the specifications describe the behavior that the system should have, but do not give any indication of the visual rendering that the two new interfaces should have? | NS-7: The acceptance criteria are not precise enough. What are the expected results?

## P1C3 Requirements and Functionalities
Requirement | Typology | Criticality | Functionality
example: NS-01 | HMI | Critical | Order reception
NS-5 | HMI | Medium | Order reception
NS-6 | Back-office | Critical | Order reception
NS-7 | HMI | Medium | Order tracking

## P1C4 Requirements Review V1
Question number | Requirement | Applicant | Criticality | Request date | Comment | State | Document version | Respondent | Response date | Response
1 | EX-1 | Martin | Critical | 2023-01-02 | A typo must have slipped in place of the WS URL? | Processed | v.1 | Adrien | 2023-01-09 | Updated spec
1 | NS-5 | You | Medium | 2023-04-20 | In the acceptance criteria, the elements to be checked for the "Cancel" button are not described. What about it? | Sent | v.1 | Édouard | 2023-04-24 | Specifications to be updated in this direction: "When clicking on "Cancel", verify that the data is not saved in the database. Then that the user returns to the previous screen."
2 | NS-6 | You | Critical | 2023-04-20 | The format of the "Adr_livr" field is not specified, what type should it be? | Sent | v.1 | Édouard | 2023-04-24 | Spec to be updated: the format must be of type TEXT.
3 | NS-7 | You | Critical | 2023-04-20 | The specification indicates the information that must be displayed, but does not describe where it should be searched? | Sent | v.1 | Édouard | 2023-04-24 | Spec to be updated: This information must be retrieved from the database. The customer name must come from the t_client table, "Nom" field. Customer identifier from t_client, "id_client" field. Order number from t_commande, "id_commande" field. The delivery address from t_commande, "Adr_livr" field.
Mail of the deliverable sharing
To: MOA, AMOA, PO CC: Project team Subject: Delivery of requirements review document
Hello, You will find attached to this email the requirements review document. Here are the key points to remember: - Requirement NS-6: The format of a field in the database is not specified. - Requirement NS-7: The specifications do not indicate where to retrieve the information in the database. I draw your attention to these warning elements: - Requirement NS-5: The acceptance criteria do not mention what should be checked for the "Cancel" button. I remain at your disposal for any further information, Sincerely, ME

## P1C5 Deliverable Email
Requirement | Applicant | Criticality | Request date | Comment | State | Document version | Respondent | Response date | Response
EX-1 | Martin | Critical | 2023-01-02 | A typo must have slipped in place of the WS URL? | Processed | v.1 | Adrien | 2023-01-09 | Updated spec
NS-5 | You | Medium | 2023-04-20 | In the acceptance criteria, the elements to be checked for the "Cancel" button are not described. What about it? | Processed | v.1 | Édouard | 2023-04-24 | Specifications to be updated in this direction: "When clicking on "Cancel", verify that the data is not saved in the database. Then that the user returns to the previous screen."
NS-6 | You | Critical | 2023-04-20 | The format of the "Adr_livr" field is not specified, what type should it be? | Processed | v.1 | Édouard | 2023-04-24 | Spec to be updated: The format must be of type TEXT.
NS-7 | You | Critical | 2023-04-20 | The specification indicates the information that must be displayed, but does not describe where it should be searched? | Processed | v.1 | Édouard | 2023-04-24 | Spec to be updated: This information must be retrieved from the database. The Customer Name must come from the t_client table, "Nom" field. Customer identifier from t_client, "id_client" field. Order number from t_commande, "id_commande" field. Delivery address from t_commande, "Adr_livr" field. For the order details part, I need to validate something before I can answer.
NS-7 | You | Critical | 2023-04-21 | Édouard's response: The display of the request details has not been specified. Point taken with the developers. | Sent | v.2
Final deliverable email
To: MOA, AMOA, PO CC: Project team Subject: Delivery of requirements review document
Hello, You will find attached to this email the final document of the requirements review. Here are the key points to remember: The elements identified on NS-5, NS-6, and part of those on NS-7 have been resolved. I draw your attention to this alert element: - Requirement NS-7: The storage method for the request details with its content and progress has not been specified. Point taken by Édouard to define this. I remain at your disposal for any further information, Sincerely, ME

## P2C1 Scenario Definition
Functionality | Requirements | Scenario | Comment | Impact
Order reception | NS-5 | - Registration of an authenticated customer order - Cancellation of order entry | CDT-2 will become obsolete with this project. It will not be possible to place an order without being authenticated. | CDT-2: Place a customer order not authenticated CDT-3: Place an authenticated customer order Autom-2: Place a customer order not authenticated Autom-3: Place an authenticated customer order
Order reception | NS-6 | - Verification of the t_commande table | This table still needs to evolve to take into account the order details. Wait for Édouard's feedback before building the scenario.
Order tracking | NS-7 | - Verification of order tracking

## P2C2 Test Methods
Scenario related to functionality | Test method | Justification
Registration of an authenticated customer order | Black box | As test automations may not be available for the start of the campaign, the tests will be performed manually.
Registration of a customer order not authenticated | Black box
Cancellation of order entry | Black box
Verification of the t_commande table | Black box
Verification of order tracking | Black box
"Order Reception" functionality - Exploratory tests | Exploratory tests | Exploratory testing session to improve test coverage.
"Order Tracking" functionality - Exploratory tests | Exploratory tests | Exploratory testing session to improve test coverage.
Customer area access | Non-regression | Critical functionality of the application, it is necessary to perform a non-regression test to verify that it has not suffered any side effects.

## P2C3 Resource Inventory
Scenario related to functionality | Environment | Justification | Tester | Justification | Test tool | Justification | Test data | Justification
- Registration of an authenticated customer order - Cancellation of order entry - Verification of the t_commande table - Verification of order tracking | ENV-2 | ENV-1 will not be available during the execution phase | You | Of the two available resources, Andy will be on leave for most of the execution phase and will be on another project afterwards. As for me, the 2 days of absence will have a very minimal impact during the phase. | Excel | Use of the existing test management tool in the company. The other tool being tested by the other team is not official, it cannot be used. | DUPONT
- Registration of a customer order not authenticated | ENV-2 | ENV-1 will not be available during the execution phase | You | Of the two available resources, Andy will be on leave for most of the execution phase and will be on another project afterwards. As for me, the 2 days of absence will have a very minimal impact during the phase. | Excel | Use of the existing test management tool in the company. The other tool being tested by the other team is not official, it cannot be used. |  | No test data required. The test case is performed in "non-authenticated" mode.

## P2C4 Step Planning
|  | October | [30 empty] | November
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Developments | bar: October 3 to October 7; October 10 to October 14
Tests | Requirements analysis | bar: October 3 to October 7
Test strategy | bar: October 10 to October 12
Design | bar: October 13 to October 14
Execution | bar: October 17 to October 20; October 25 to October 28
Report | bar: October 31
Production release | bar: November 21
Absences | Andy | bar: October 17 to October 21; October 24 to October 28
You | bar: October 21; October 24

## P2C5 Recommendation
Recommendation email
To: MOA, AMOA, PO CC: Project team Subject: Recommendation | Hello, Please find attached to this email the test strategy for the CLC project in version 1.0.0. Here are the key points to remember: - Test automates cannot be used during the execution phase. They will need to be updated following the test campaign. - Andy's vacation during the execution phase. I would like to draw your attention to these warning elements: - The solution for recording order information arrived only 3 days before the end of development. This presents a risk of delaying the start of execution. --> This risk could be absorbed by the significant delay (1 month) between the planned end of execution and the production release. I remain at your disposal for any further information, Sincerely, ME
Hello, Please find attached to this email the test strategy for the CLC project in version 1.0.0. Here are the key points to remember: - Test automates cannot be used during the execution phase. They will need to be updated following the test campaign. - Andy's vacation during the execution phase. I would like to draw your attention to these warning elements: - The solution for recording order information arrived only 3 days before the end of development. This presents a risk of delaying the start of execution. --> This risk could be absorbed by the significant delay (1 month) between the planned end of execution and the production release. I remain at your disposal for any further information, Sincerely, ME

## P3C1 Preparation of the Specifi
Requirement ID | Requirement name | Version | Criticality | Status | Category | Description
NS-5 | Order UI | v1 | Major | Approved | Functional | Order UI to allow customers to place and receive their orders.
NS-6 | Order table | v1 | Major | Approved | Technical | Database table to store order information.
NS-7 | Tracking UI | v1 | Major | Approved | Functional | Tracking UI to allow customers to track their order.

## P3C2 Test Case Writing
Explanations
CDT-2: Place an order as an unauthenticated customer Description: This test case tests placing an order by a customer who is not authenticated on the site Prerequisites: Site in v.1.1.0 Status: Obsolete |  |  | The evolution of this test case consists of changing the status of the test case to "Obsolete". In the specifications, it is indicated that orders are now exclusively from the customer area, and therefore the customer must be authenticated.
# Steps | Operating procedure | Expected result
1 | Access the website via the URL www.nousommesalapage.bigdeal.fr | The website homepage is displayed
2 | In the left menu, check for the presence of the "Order" link | Link present
3 | Click on the "Order" link | Redirection to the "Order" page
4 | Check for the presence of the banner at the top of the page "You are not authenticated in the customer area, the number displayed is that of the call center, please authenticate to find out the number of your dedicated agency" | The banner is compliant
5 | Verify that the phone number displayed is that of the call center "0 880 999 999" | The number displayed is correct
CDT-3: Place an order as an authenticated customer Description: This test case tests placing an order by a customer who is authenticated on the site Prerequisites: Site in v.1.1.0 Status: Approved |  |  | The evolution on this test case consists of modifying the access mode to the command from step 7. In the specifications, it is indicated that this is now done from the customer area after the customer's authentication. After modifying the access path, we remove the steps mentioning the information banner, and the phone number to call. To add the form steps.
# Steps | Operating procedure | Expected result
1 | Access the website via the URL www.nousommesalapage.bigdeal.fr | The website homepage is displayed
2 | Verify the presence of the "Customer Area" link at the top right of the site's homepage | The "Customer Area" link is present
3 | Click on "Customer Area" | Display of the login page to the customer area
4 | In the "Login" field, enter "dupont@st.fr" | Login entered
5 | In the "Password" field, enter "Mvp23" | Password entered
6 | Click on "Connection" | Display of Dupont's customer area
7 | On the main page of the customer area, verify the presence of the "Order" link | Link present
8 | Click on the "Order" link | Redirection to the "Order" page
9 | Verify the presence of the form | The form is present
10 | Select the following value from the "Paper Type" drop-down list: - Standard paper (60 - 90 g/m2) | The value is selected
11 | Select the following value from the "Format" drop-down list: - A4 | The value is selected
12 | Select the following value from the "Number of reams" drop-down list: - 1 | The value is selected
13 | Verify the presence of the free field "Delivery address" | The field is present
14 | Enter the value "2 Rue de Schomberg, 75004 Paris" in the free field | The address is entered
15 | Click on "Save" | Verify the display of the message “Your order has been successfully registered - Order number”
CDT-4: Verify the order interface Description: This test case allows you to verify the order interface Prerequisites: Site in v.1.1.0 Status: Approved |  |  | For this case, it is a matter of verifying that the interface is compliant. We will not try to save data, just to check that all the specified fields and values are present. If the interface is not compliant, the registration of an order will therefore not be possible, or not correct at least.
# Steps | Operating procedure | Expected result
1 | Access the website via the URL www.nousommesalapage.bigdeal.fr | The website homepage is displayed
2 | Verify the presence of the "Customer Area" link at the top right of the site's homepage | The "Customer Area" link is present
3 | Click on "Customer Area" | Display of the login page to the customer area
4 | In the "Login" field, enter "dupont@st.fr" | Login entered
5 | In the "Password" field, enter "Mvp23" | Password entered
6 | Click on "Connection" | Display of Dupont's customer area
7 | On the main page of the customer area, verify the presence of the "Order" link | Link present
8 | Click on the "Order" link | Redirection to the "Order" page
9 | Verify the presence of the form | The form is present
10 | Verify that the "Paper Type" drop-down list has the following values: - Standard paper (60 - 90 g/m2) - Recycled paper - Photo paper | The values in the drop-down list are compliant
11 | Verify that the "Format" drop-down list has the following values: - A0 - A1 - A2 - A3 - A4 - A5 - A6 | The values in the drop-down list are compliant
12 | Verify that the "Number of reams" drop-down list has the following values: - 1 - 2 - 3 - 4 - 5 | The values in the drop-down list are compliant
13 | Verify the presence of the free field "Delivery address" | The field is present
| Verify the presence of the "Save" button | The button is present
| Verify the presence of the "Cancel" button | The button is present
CDT-5: Verify the structure of the t_commande table Description: This test case allows you to verify that the t_commande table has been created correctly Prerequisites: Site in v.1.1.0 Status: Approved |  |  | As with the order interface, we will create a test case to verify that the structure of the table is compliant. If it is not, we will not be able to save an order
# Steps | Operating procedure | Expected result
1 | Connect to the site's database | Authentication to the database successful
2 | Execute the following SQL query: SELECT * FROM T_COMMANDE | Display of the content of the t_commande table
3 | Verify the presence of the "id_commande" column | The column is present
4 | Verify that the "id_commande" column is identified as the primary key | the column is the primary key
5 | Verify that the "id_commande" column is in "Numeric" format | The format of the column is compliant
6 | Verify that the "id_commande" column is mandatory | The "id_commande" column is mandatory
7 | Verify the presence of the "id_client" column | The column is present
8 | Verify that the "id_client" column is in "Numeric" format | The format of the column is compliant
9 | Verify that the "id_client" column is mandatory | The column is indicated as mandatory
10 | Verify the presence of the "Nb_rames" column | The column is present
11 | Verify that the "Nb_rames" column is in "Numeric" format | The format of the column is compliant
12 | Verify that the "Nb_rames" column is mandatory | The column is indicated as mandatory
13 | Verify the presence of the "Adr_livr" column | The column is present
14 | Verify that the "Adr_livr" column is in "Text" format | The format of the column is compliant
15 | Verify that the "Adr_livr" column is mandatory | The column is indicated as mandatory
16 | Verify the presence of the "Typ_pap" column | The column is present
17 | Verify that the "Typ_pap" column is in "Text" format | The format of the column is compliant
18 | Verify that the "Typ_pap" column is mandatory | The column is indicated as mandatory
19 | Verify the presence of the "Form_pap" column | The column is present
20 | Verify that the "Form_pap" column is in "Text" format | The format of the column is compliant
21 | Verify that the "Form_pap" column is mandatory | The column is indicated as mandatory
CDT-6: Verify order storage Description: This test case allows you to test that the recording of orders is correct Prerequisites: Site in v.1.1.0 Have placed an order and know its number Status: Approved |  |  | Following the placing of an order, the data will be saved. We therefore need to create a test case to verify that the data entered on the interface is correctly reflected in the database.
# Steps | Operating procedure | Expected result
1 | Connect to the site's database | Authentication to the database successful
2 | Execute the following SQL query: SELECT * FROM T_COMMANDE WHERE id_commande = "Order number" | Display of data linked to the order
3 | Verify that the id_commande is equal to the "order number" | The field value is compliant
4 | Verify that the id_client is equal to "10001" | The field value is compliant
5 | Verify that the Nb_rame is equal to "1" | The field value is compliant
6 | Verify that the Adr_Livr is equal to "2 Rue de Schomberg, 75004 Paris" | The field value is compliant
7 | Verify that the Typ_Pap is equal to "Standard paper (60 - 90 g/m2)" | The field value is compliant
8 | Verify that the Form_pap is A4 | The field value is compliant
CDT-7: Verify the order tracking interface Description: This test case allows you to verify the order tracking interface Prerequisites: Site in v.1.1.0 Have at least one order on the client Status: Approved |  |  | As with the order interface. We create a test case to verify that the order tracking interface complies with expectations.
# Steps | Operating procedure | Expected result
1 | Access the website via the URL www.nousommesalapage.bigdeal.fr | The website homepage is displayed
2 | Verify the presence of the "Customer Area" link at the top right of the site's homepage | The "Customer Area" link is present
3 | Click on "Customer Area" | Display of the login page to the customer area
4 | In the "Login" field, enter "dupont@st.fr" | Login entered
5 | In the "Password" field, enter "Mvp23" | Password entered
6 | Click on "Connection" | Display of Dupont's customer area
7 | On the main page of the customer area, verify the presence of the link "Track my orders" | Link present
8 | Click on the link "Track my orders" | Redirection to the "Order" page
9 | Verify the presence of the customer's name | The form is present
10 | Verify the presence of the customer's identifier, to the right of their name | The values in the drop-down list are compliant
11 | Verify the presence of the order number | The values in the drop-down list are compliant
12 | Verify the presence of the delivery address | The values in the drop-down list are compliant
13 | Verify the presence of the order details with the type of paper and the format of the paper | The field is present
CDT-8: Verify the order tracking information Description: This test case allows you to verify that the information returned on the order tracking interface is compliant Prerequisites: Site in v.1.1.0 Have at least one order on the client Status: Approved |  |  | This involves creating a test case to verify that the information displayed on the interface is compliant. This information often comes from a database. I have deliberately written here where to look for these values rather than writing them in hard, because it is another way of writing test cases, in order to make them as "modular" and "reusable" as possible. We therefore verify that all the information displayed on the screen complies with that which is stored in the database.
# Steps | Operating procedure | Expected result
1 | Connect to the site's database | Authentication to the database successful
2 | Execute the following SQL query: SELECT * FROM t_commande INNER JOIN t_client on t_client.id_client = t_commande.id_client WHERE t_commande,id_commande = "Order number" | Display of query results
3 | Access the website via the URL www.nousommesalapage.bigdeal.fr | The website homepage is displayed
4 | Verify the presence of the "Customer Area" link at the top right of the site's homepage | The "Customer Area" link is present
5 | Click on "Customer Area" | Display of the login page to the customer area
6 | In the "Login" field, enter "dupont@st.fr" | Login entered
7 | In the "Password" field, enter "Mvp23" | Password entered
8 | Click on "Connection" | Display of Dupont's customer area
9 | On the main page of the customer area, verify the presence of the link "Track my orders" | Link present
10 | Click on the link "Track my orders" | Redirection to the "Order" page
11 | Verify that the customer's name is equal to the value in the database of "t_client.Nom" | The form is present
12 | Verify that the customer's identifier is equal to the value in the database of "t_client._id_client" | The values in the drop-down list are compliant
13 | Verify that the order number matches the value in the database for "t_commande.id_commande" | The values in the drop-down list are compliant
14 | Verify that the delivery address matches the value in the database for "t_commande.Adr_livr" | The values in the drop-down list are compliant
15 | Verify that the paper type matches the value in the database for "t_commande.Typ_pap" | The field is present
16 | Verify that the paper format matches the value in the database for "t_commande.Form_pap" | The field is present
17 | Verify that the number of reams matches the value in the database for "t_commande.Nbr_ram" | The field is present
CDT-9: Cancel an order Description: This test case tests the placing of an order by a customer who is authenticated on the site Prerequisites: Site in v.1.1.0 Status: Approved |  |  | This test case is created to verify that during the order process, clicking on the "Cancel" button does not result in any database records being made.
# Steps | Operating procedure | Expected result
1 | Access the website via the URL www.nousommesalapage.bigdeal.fr | The website homepage is displayed
2 | Verify the presence of the "Customer Area" link at the top right of the site's homepage | The "Customer Area" link is present
3 | Click on "Customer Area" | Display of the login page to the customer area
4 | In the "Login" field, enter "dupont@st.fr" | Login entered
5 | In the "Password" field, enter "Mvp23" | Password entered
6 | Click on "Connection" | Display of Dupont's customer area
7 | On the main page of the customer area, verify the presence of the "Order" link | Link present
8 | Click on the "Order" link | Redirection to the "Order" page
9 | Verify the presence of the form | The form is present
10 | Select the following value from the "Paper Type" drop-down list: - Standard paper (60 - 90 g/m2) | The value is selected
11 | Select the following value from the "Format" drop-down list: - A4 | The value is selected
12 | Select the following value from the "Number of reams" drop-down list: - 1 | The value is selected
13 | Verify the presence of the free field "Delivery address" | The field is present
14 | Enter the value "2 Rue de Schomberg, 75004 Paris" in the free field | The address is entered
15 | Click on "Cancel" | Verify the display of the message “Your order has not been saved, you will be redirected to the customer area”
16 | Connect to the site's database | Authentication to the database successful
17 | Execute the following SQL query: SELECT * FROM t_commande order by id_commande desc; | Display of the query result
18 | Verify that no new order has been saved in the database | No new order has been saved

## P3C3 Assembly into Scenarios
Scenario number | Scenario name | Associated requirement | Prerequisites | Test cases | Explanations
SC-1 | Create a scenario | EX-1 | Have defined my scenario | CDT-1 CDT-2 CDT-3
SC-1 | Registration of an authenticated customer order | NS-5 NS-6 | 1. The site must be in version 1.1.0 2. Have a customer | CDT-5: Verify structure of the t_commande table CDT-1 - Access the customer area CDT-4: Verify the order interface CDT-3: Place an authenticated customer order CDT-6: Verify order storage | For this scenario, we assemble the test cases related to the order. It is interesting to first verify the structure of the database. If it is incorrect, it is very likely that it will not be possible to continue the scenario. Then, we guide the tester to the order screen by indicating how to access the customer area. Then we check the order interface. Like the database, if the information is not correct on the interface, it will not be necessary to continue to the registration. Then, finally, we enter an order and check the impact in the database.
SC-2 | Cancellation of order entry | NS-5 NS-6 | 1. The site must be in version 1.1.0 2. Have a customer | CDT-1 - Access the customer area CDT-8: Cancel an order | For this scenario, we take the test case that will guide the tester to the customer area. Then our test case that will cancel the entry of an order and verify that we do not save it in the database.
SC-3 | Verification of order tracking | NS-7 | 1. The site must be in version 1.1.0 2. Have a customer who already has at least one order | CDT-1 - Access the customer area CDT-7: Verify the order tracking interface CDT-9: Verify the order tracking information | Finally, for this third scenario, the subtlety arises in the prerequisites, where it is necessary to have at least one order in the database for the customer used. After that, as for the registration, we check that the order tracking interface is compliant, before verifying that the information retrieved from the database is also compliant.

## P3C4 Presentation of the Speci
Requirements coverage | Explanations
All the requirements to be tested are covered by at least one test case. NS-5: Create order HMI by CDT-5, CDT-4, CDT-3, CDT-8 NS-6: Create t_commande table by CDT-6 NS-7: Create order tracking HMI by CDT-7 and CDT-9 | List all the requirements that are tested during the campaign, and display the test cases that cover them
Scenarios
The planned scenarios are: - Registration of an authenticated customer order - Cancellation of order entry - Verification of order tracking | Display all the scenarios that you have planned to test
Testing methods
Three testing methods will be used: - Functional tests (Black box) - Exploratory tests - Non-regression tests
Datasets
Only one dataset will be needed: - Client DUPONT | Share the datasets you are going to use
Reminder of risks and recommendations
- The solution for recording order information arrived only 3 days before the end of development. This presents a risk of delaying the start of execution, --> This risk could be absorbed by the significant delay (1 month) between the planned end of execution and the production release. | Share the risks again and what you have put in place to prevent them
Appendices
The test case document is available at this link. | Allow those who wish to find your test case document so they can review it if they wish