## P1C2 Functional Specifications
Synthesis | Questions | Points of attention
Write your synthesis here with the issues and purpose of the project | Note your questions here | Raise your points of attention here

## P1C3 Requirements and Functionality
Requirement | Typology | Criticality | Functionality
example: NS-01 | HMI | Critical | Order reception

## P1C4 Requirements Review V1
Question number | Requirement | Requester | Criticality | Request date | Comment | State | Document version | Responder | Response date | Response
1 | EX-1 | Martin | Critical | 2023-01-02 | Must a typo have slipped in place of the WS URL? | Processed | v.1 | Adrien | 2023-01-09 | Updated spec
Email sharing the deliverable
To: MOA, AMOA, PO CC: Project team Subject: Delivery of requirements review document
Hello, You will find attached to this email the requirements review document. Here are the key points to remember: - Requirement NS-6: The format of a field in the database is not specified. - Requirement NS-7: The specifications do not indicate where to retrieve the information in the database. I draw your attention to these warning elements: - Requirement NS-5: The acceptance criteria do not mention what should be verified for the "Cancel" button. I remain at your disposal for any further information, Sincerely, ME

## P1C5 Deliverable Email
Final deliverable email
To: MOA, AMOA, PO CC: Project team Subject: Delivery of requirements review document
Write your email here presenting the consolidated requirements review

## P2C1 Scenario Definition
Functionality | Requirements | Scenario | Comment | Impact
Order reception | NS-5 | - Registration of an authenticated customer order - Cancellation of order entry | CDT-2 will become obsolete with this project. It will not be possible to place an order without being authenticated. | CDT-2: Place a non-authenticated customer order CDT-3: Place an authenticated customer order Autom-2: Place a non-authenticated customer order Autom-3: Place an authenticated customer order

## P2C2 Test Methods
Scenario related to functionality | Test method | Justification

## P2C3 Resource Inventory
Scenario related to functionality | Environment | Justification | Tester | Justification | Test tool | Justification | Test data | Justification
[5 empty] | Excel | Use of the existing test management tool in the company. The other tool being tested by the other team is not official, it cannot be used. | DUPONT
[5 empty] | Excel | Use of the existing test management tool in the company. The other tool being tested by the other team is not official, it cannot be used. |  | No test data required. The test case is carried out in "non-authenticated" mode.

## P2C4 Step Planning
|  | October | [30 empty] | November
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Developments
Tests | Requirements analysis | bar: October 3 to October 7
Test strategy
Design
Execution
Review
Release to production
Absences | Andy
You

## P2C5 Recommendation
Recommendation email
To: MOA, AMOA, PO CC: Project team Subject: Recommendation | Hello, Please find attached to this email the test strategy for the CLC project in version 1.0.0. Here are the key points to remember: - Test automation cannot be used during the execution phase. They will need to be updated following the test campaign. - Andy's vacation during the execution phase. I draw your attention to these warning elements: - The solution for recording order information arrived only 3 days before the end of development. This presents a risk of delaying the start of execution. --> This risk could be absorbed by the significant delay (1 month) between the planned end of execution and the production release. Please do not hesitate to contact me if you require any further information. Sincerely, ME
Write your email here presenting your recommendation

## P3C1 Preparation of Specification
Requirement ID | Requirement Name | Version | Criticality | Status | Category | Description
NS-5 | Order UI | v1 | Major | Approved | Functional | Order UI to allow customers to place and receive their orders.

## P3C2 Test Case Writing
Explanations
CDT-2: Place an order as an unauthenticated customer Description: This test case tests placing an order by a customer who is not authenticated on the site Prerequisites: Site in v.1.1.0 Status: Obsolete |  |  | The change to this test case is to modify the status of the test case to "Obsolete." In the specifications, it is indicated that orders are now exclusively from the customer area, and therefore the customer must be authenticated.
# Steps | Operating procedure | Expected result
1 | Access the website via the URL www.nousommesalapage.bigdeal.fr | The website homepage is displayed
2 | In the left menu, verify the presence of the "Order" link | Link present
3 | Click on the "Order" link | Redirection to the "Order" page
4 | Verify the presence of the banner at the top of the page "You are not authenticated in the customer area, the number displayed is that of the call center, please authenticate to find out the number of your dedicated agency" | The banner is compliant
5 | Verify that the phone number displayed is that of the call center "0 880 999 999" | The number displayed is correct
CDT-3: Place an order as an authenticated customer Description: This test case tests placing an order by a customer who is authenticated on the site Prerequisites: Site in v.1.1.0 Status: Approved |  |  | The change to this test case is to modify the method of accessing the order from step 7. In the specifications, it is indicated that this is now done from the customer area after the customer's authentication. After modifying the access path, we remove the steps mentioning the information banner, and the phone number to call. To add the form steps.
# Steps | Operating procedure | Expected result
1 | Access the website via the URL www.nousommesalapage.bigdeal.fr | The website homepage is displayed
2 | Verify the presence of the "Customer Area" link at the top right of the website homepage | The "Customer Area" link is present
3 | Click on "Customer Area" | Display of the customer area login page
4
5
6
7
8
9
10
11
12
13
14
15
CDT-4: Verify the order interface Description: This test case verifies the order interface Prerequisites: Site in v.1.1.0 Status: Approved |  |  | For this case, it is a matter of verifying that the interface is compliant. We will not try to record data, just to check that all the specified fields and values are present. If the interface is not compliant, recording an order will therefore not be possible, or not correct at least.
# Steps | Operating procedure | Expected result
1 | Access the website via the URL www.nousommesalapage.bigdeal.fr | The website homepage is displayed
2 | Verify the presence of the "Customer Area" link at the top right of the website homepage | The "Customer Area" link is present
3 | Click on "Customer Area" | Display of the customer area login page
4 | In the "Login" field, enter "dupont@st.fr" | Login entered
5 | In the "Password" field, enter "Mvp23" | Password entered
6 | Click on "Connection" | Display of Dupont's customer area
7 | On the main page of the customer area, check for the "Order" link | Link present
8 | Click on the "Order" link | Redirection to the "Order" page
9 | Check for the presence of the form | The form is present
10 | Verify that the "Paper Type" dropdown list has the following values: - Standard paper (60 - 90 g/m2) - Recycled paper - Photo paper | The values in the dropdown list are correct
11 | Verify that the "Format" dropdown list has the following values: - A0 - A1 - A2 - A3 - A4 - A5 - A6 | The values in the dropdown list are correct
12 | Verify that the "Number of reams" dropdown list has the following values: - 1 - 2 - 3 - 4 - 5 | The values in the dropdown list are correct
13 | Check for the presence of the free text field "Delivery address" | The field is present
| Check for the presence of the "Save" button | The button is present
| Check for the presence of the "Cancel" button | The button is present
CDT-5: Verify structure of the t_commande table Description: This test case verifies that the t_commande table was created correctly Prerequisites: Site in v.1.1.0 Status: Approved |  |  | As with the order interface, we will create a test case to verify that the structure of the table is correct. If it is not, we will not be able to save an order
# Steps | Operating procedure | Expected result
1 | Connect to the site's database | Authentication to the database successful
2 | Execute the following SQL query: SELECT * FROM T_COMMANDE | Display of the contents of the t_commande table
3 | Verify the presence of the "id_commande" column | The column is present
4 | Verify that the "id_commande" column is identified as the primary key | the column is the primary key
5 | Verify that the "id_commande" column is in "Numeric" format | The column format is correct
6 | Verify that the "id_commande" column is mandatory | The "id_commande" column is mandatory
7 | Verify the presence of the "id_client" column | The column is present
8 | Verify that the "id_client" column is in "Numeric" format | The column format is correct
9 | Verify that the "id_client" column is mandatory | The column is indicated as mandatory
10 | Verify the presence of the "Nb_rames" column | The column is present
11 | Verify that the "Nb_rames" column is in "Numeric" format | The column format is correct
12 | Verify that the "Nb_rames" column is mandatory | The column is indicated as mandatory
13 | Verify the presence of the "Adr_livr" column | The column is present
14 | Verify that the "Adr_livr" column is in "Text" format | The column format is correct
15 | Verify that the "Adr_livr" column is mandatory | The column is indicated as mandatory
16 | Verify the presence of the "Typ_pap" column | The column is present
17 | Verify that the column "Typ_pap" is in "Text" format | The column format is correct
18 | Verify that the "Typ_pap" column is mandatory | The column is indicated as mandatory
19 | Verify the presence of the "Form_pap" column | The column is present
20 | Verify that the "Form_pap" column is in "Text" format | The column format is correct
21 | Verify that the "Form_pap" column is mandatory | The column is indicated as mandatory
CDT-6: Verify order storage Description: This test case tests that the recording of orders is correct Prerequisites: Site in v.1.1.0 Have placed an order and know its number Status: Approved |  |  | Following the placing of an order, the data will be saved. We therefore need to create a test case to verify that the data entered on the interface is correctly reflected in the database.
# Steps | Operating procedure | Expected result
1 | Connect to the site's database | Authentication to the database successful
2 | Execute the following SQL query: SELECT * FROM T_COMMANDE WHERE id_commande = "Order number" | Display of data related to the order
3 | Verify that the id_commande is equal to the "order number" | The value of the field is correct
4 | Verify that the id_client is equal to "10001" | The value of the field is correct
5 | Verify that the Nb_rame is equal to "1" | The value of the field is correct
6 | Verify that the Adr_Livr is equal to "2 Rue de Schomberg, 75004 Paris" | The value of the field is correct
7 | Verify that the Typ_Pap is equal to "Standard paper (60 - 90 g/m2)" | The value of the field is correct
8 | Verify that Form_pap equals A4 | The value of the field is correct
CDT-7: Verify the order tracking interface Description: This test case verifies the order tracking interface Prerequisites: Site in v.1.1.0 Have at least one order on the client Status: Approved |  |  | As with the order interface. We create a test case to verify that the order tracking interface conforms to expectations.
# Steps | Operating procedure | Expected result
1 | Access the website via the URL www.nousommesalapage.bigdeal.fr | The website homepage is displayed
2 | Verify the presence of the "Customer Area" link at the top right of the website homepage | The "Customer Area" link is present
3 | Click on "Customer Area" | Display of the customer area login page
4 | In the "Login" field, enter "dupont@st.fr" | Login entered
5 | In the "Password" field, enter "Mvp23" | Password entered
6 | Click on "Connection" | Display of Dupont's customer area
7 | On the main page of the customer area, verify the presence of the "Track my orders" link | Link present
8 | Click on the "Track my orders" link | Redirection to the "Order" page
9 | Verify the presence of the customer's name | The form is present
10 | Verify the presence of the customer's ID, to the right of their name | The values in the dropdown list are correct
11 | Verify the presence of the order number | The values in the dropdown list are correct
12 | Verify the presence of the delivery address | The values in the dropdown list are correct
13 | Verify the presence of the order details with the paper type and paper format | The field is present
CDT-8: Verify the order tracking information Description: This test case verifies that the information displayed on the order tracking interface is correct Prerequisites: Site in v.1.1.0 Have at least one order on the client Status: Approved |  |  | This involves creating a test case to verify that the information displayed on the interface is correct. This information often comes from a database. I have deliberately written here where to look for these values rather than writing them directly, because it is another way of writing test cases, in order to make them as "modular" and "reusable" as possible. We therefore verify that all the information displayed on the screen is consistent with that stored in the database.
# Steps | Operating procedure | Expected result
1 | Connect to the site's database | Authentication to the database successful
2 | Execute the following SQL query: SELECT * FROM t_commande INNER JOIN t_client on t_client.id_client = t_commande.id_client WHERE t_commande,id_commande = "Order number" | Displaying the query results
3 | Access the website via the URL www.nousommesalapage.bigdeal.fr | The website homepage is displayed
4 | Verify the presence of the "Customer Area" link at the top right of the website homepage | The "Customer Area" link is present
5 | Click on "Customer Area" | Display of the customer area login page
6 | In the "Login" field, enter "dupont@st.fr" | Login entered
7 | In the "Password" field, enter "Mvp23" | Password entered
8 | Click on "Connection" | Display of Dupont's customer area
9 | On the main page of the customer area, verify the presence of the "Track my orders" link | Link present
10 | Click on the "Track my orders" link | Redirection to the "Order" page
11 | Verify that the customer's name matches the value in the database for "t_client.Nom" | The form is present
12 | Verify that the customer's ID matches the value in the database for "t_client._id_client" | The values in the dropdown list are correct
13 | Verify that the order number matches the value in the database for "t_commande.id_commande" | The values in the dropdown list are correct
14 | Verify that the delivery address matches the value in the database for "t_commande.Adr_livr" | The values in the dropdown list are correct
15 | Verify that the paper type matches the value in the database for "t_commande.Typ_pap" | The field is present
16 | Verify that the paper format matches the value in the database for "t_commande.Form_pap" | The field is present
17 | Verify that the number of reams matches the value in the database for "t_commande.Nbr_ram" | The field is present
CDT-9: Cancel an order Description: This test case tests the placing of an order by a client who is authenticated on the site Prerequisites: Site in v.1.1.0 Status: Approved |  |  | This test case is created to verify that during the order process, clicking on the "Cancel" button does not result in any database entries.
# Steps | Operating procedure | Expected result
1 | Access the website via the URL www.nousommesalapage.bigdeal.fr | The website homepage is displayed
2 | Verify the presence of the "Customer Area" link at the top right of the website homepage | The "Customer Area" link is present
3 | Click on "Customer Area" | Display of the customer area login page
4 | In the "Login" field, enter "dupont@st.fr" | Login entered
5 | In the "Password" field, enter "Mvp23" | Password entered
6 | Click on "Connection" | Display of Dupont's customer area
7 | On the main page of the customer area, check for the "Order" link | Link present
8 | Click on the "Order" link | Redirection to the "Order" page
9 | Check for the presence of the form | The form is present
10 | Select the following value from the "Paper type" drop-down list: - Standard paper (60 - 90 g/m2) | The value is selected
11 | Select the following value from the "Format" drop-down list: - A4 | The value is selected
12 | Select the following value from the "Number of reams" drop-down list: - 1 | The value is selected
13 | Check for the presence of the free text field "Delivery address" | The field is present
14 | Enter the value "2 Rue de Schomberg, 75004 Paris" in the free text field | The address is entered
15 | Click on "Cancel" | Verify the display of the message “Your order has not been saved, you will be redirected to the customer area”
16 | Connect to the site's database | Authentication to the database successful
17 | Execute the following SQL query: SELECT * FROM t_commande order by id_commande desc; | Displaying the query result
18 | Verify that no new order has been saved in the database | No new order has been saved

## P3C3 Assembly into Scenarios
Scenario number | Scenario name | Associated requirement | Prerequisites | Test cases | Explanations
SC-1 | Create a scenario | EX-1 | Have defined my scenario | CDT-1 CDT-2 CDT-3

## P3C4 Presentation of Specification
Requirements coverage | Explanations
Scenarios | Explanations
Test methods | Explanations
Data sets | Explanations
Reminder of risks and recommendations | Explanations
Appendices | Explanations